## Sheet1
Date: | 8.05.2021 |  |  |  |  | Status
Project name: | Biddo |  |  |  |  | pass | 18
Developer: | http://mamun.thesoftking.com/biddo/ |  |  |  |  | fail | 2
Perform by: | Ayesha |  |  |  |  | comment | 1
Developer: | Mamun Vai
User Panel
Test Number | Test Case | Test Steps | Module | Actual Results | Expected Results | Pass/Fail | Comment
1 | Frontend | Manual | Header | all data are clickable | all data are clickable | pass
1.1 |  |  | Body | all data are clickable | all data are clickable | pass
1.2 |  |  | Footer | all data are clickable | all data are clickable | pass
2 | User Registration as Publisher | Manual | Registration | valid data are working fine | Registration is successful | pass
2.1 | User Login |  | Login | valid data are working fine | login is successful | pass
3 | User Dashboard | Manual | Dashboard | all data are clickable | all data are clickable | pass
3.1 |  |  | Profile | all data are clickable | all data are clickable | pass
3.2 |  |  | Deposit | issue with manual method | all data are clckable | fail | username1 ¦¦ Username@1
3.3 |  |  | Transaction log | all the data are working | all the data are working fine | pass
3.4 |  |  | Support Tickets | Support Tickets do not support the .docx file but it written supported here | Support Tickets need to support the .docx file | fail
5 | Frontend | Console | Full frontend | all data are ok | all data are clickable | pass
6 | Responsive |  |  | Most Popular Advertising formats | 320 | pass
Admin Panel
1 | Dashboard | Manual | Dashboard | all data are clickable | all data are clickable | pass
4.1 |  |  | banned Advertisers | banned Advertisers is not showing to the banned Advertisers list | banned Advertisers need to show to the list | pass
5.1 |  |  |  | banned publisher is not showing to the banned Advertisers list | banned publisher need to show to the list | pass
6 | Deposits system |  | pending deposits | the action button is not working | it needs to show the detail of pending deposit | pass
7 | Support ticket |  | pending tickets | the action button is not working | it needs to show the detail of pending ticket | pass
8 | Extension |  | Extensions | the action button is not working | it needs to edit | pass
9 | Manage section |  | Benefits Section | not editable | the text need to change | pass
5 | Admin panel | Console | admin panel | all data are ok | all data are clickable | pass